## Feuille 1
Weekly team plan | (Deliverable 3)
Tasks | Weight | Members in charge
Meetings and Team Management | 2020-01-05
Record decisions(during meetings) | 3 | Bruno, Younes
Meeting Schedule and planning | 1 | Matthew
Agenda | 3 | Matthew, Bruno
Conduct and overview team meetings | 2 | Matthew
Scheduling meetings with client | 5 | Amir
Research | 2020-04-05
Client use cases | 5 | Matthew, Valentina, Younes
Understanding how client's current system works | 5 | Matthew, Valentina, Younes
Forms & documents used by client | 4 | Amir
Documentation | 2020-02-05
Narrative description | 4 | Bruno
Business problem | 2 | Amir
Executive overview | 4 | Matthew
Work cited/ Bibliography | 3 | Bruno
Spelling, grammar and formatting | 3 | Matthew, Valentina
Keeping GitHub repo up to date | 2 | Valentina
Weekly team plan | 2 | Valentina
Project Plan | 2 | Younes
Charts and Diagrams | 4
System diagram (Entire system) | 4 | Everyone
Use cases templates (at least 4) | 4 | Everyone
UML diagrams (Activity&sequence/2 use cases) | 4 | Everyone
Statechart diagram (1 significant class) | 4 | Everyone
Class diagram (Entire system) | 4 | Everyone